## Timeline
EU AML Package — prospective timeline to live dates (Level 1 + Level 2/3)
Prepared 23 Jul 2026 from AMLA/Commission official sources. Best case = user's 3+3+3 model; Realistic = longer Commission stage. Not legal advice.
LEVEL 1 — agreed texts (in force since 9 Jul 2024)
AMLR — Regulation (EU) 2024/1624 (single rulebook: CDD, BO, PEPs, obliged entities) | [6 empty] | Applies 10 Jul 2027 (directly applicable; no transposition)
AMLD6 — Directive (EU) 2024/1640 (supervision, FIUs, BO registers) | [6 empty] | Transposition deadline 10 Jul 2027 (Art. 74: BO registers 10 Jul 2026)
AMLAR — Regulation (EU) 2024/1620 (AMLA) | [6 empty] | AMLA operational since Jul 2025; direct supervision of ~40 entities from 2028 (selection 2027)
LEVEL 2/3 — AMLA instruments: consultations and projected live dates
# | Type | Legal basis | Instrument | Consult. opens | Consult. closes | Status | AMLA final → EC (best) | EC adoption (best) | Scrutiny ends (best) | LIVE — best case | AMLA final → EC (real.) | EC adoption (real.) | Scrutiny ends (real.) | LIVE — realistic | Risk vs 10 Jul 2027
1 | RTS | AMLAR 12(7) | Risk assessment for selection for direct supervision | — | — | Final report 18 Dec 2025 (EBA-consulted) | 2025-12-18 | 2026-03-18 | 2026-06-18 | 2026-07-08 | 2025-12-18 | 2026-06-18 | 2026-09-18 | 2026-10-18 | OK
2 | RTS | AMLD 40(2) | Inherent & residual risk profile of obliged entities (financial sector) | — | — | Final report 18 Dec 2025 (EBA-consulted) | 2025-12-18 | 2026-03-18 | 2026-06-18 | 2026-07-08 | 2025-12-18 | 2026-06-18 | 2026-09-18 | 2026-10-18 | OK
3 | ITS | AMLAR 15(3) | Cooperation within supervisory system (direct supervision) | 2025-12-16 | 2026-01-27 | Consultation closed; final expected Q3 2026 | 2026-04-27 | 2026-07-27 | n/a | 2026-08-16 | 2026-05-27 | 2026-11-27 | n/a | 2026-12-27 | OK
4 | RTS | AMLD 53(10) | Pecuniary sanctions, administrative measures, periodic penalty payments | 2026-02-09 | 2026-03-09 | Consultation closed; final expected Q3 2026 | 2026-06-09 | 2026-09-09 | 2026-12-09 | 2026-12-29 | 2026-07-09 | 2027-01-09 | 2027-04-09 | 2027-05-09 | Tight (<3m before application)
5 | RTS | AMLR 28(1) | Customer Due Diligence (standard / simplified / enhanced) | 2026-02-09 | 2026-05-08 | Consultation closed; final expected Q3 2026 | 2026-08-08 | 2026-11-08 | 2027-02-08 | 2027-02-28 | 2026-09-08 | 2027-03-08 | 2027-06-08 | 2027-07-08 | Tight (<3m before application)
6 | RTS | AMLR 19(9) | Business relationships, occasional & linked transactions, lower thresholds | 2026-02-09 | 2026-05-08 | Consultation closed; final expected Q3 2026 | 2026-08-08 | 2026-11-08 | 2027-02-08 | 2027-02-28 | 2026-09-08 | 2027-03-08 | 2027-06-08 | 2027-07-08 | Tight (<3m before application)
7 | RTS | AMLR 16(4), 17(3) | Group-wide minimum requirements; third-country branches/subsidiaries | 2026-04-16 | 2026-06-15 | Consultation closed; AMLA to submit to EC by 30 Sep 2026 | 2026-09-15 | 2026-12-15 | 2027-03-15 | 2027-04-04 | 2026-10-15 | 2027-04-15 | 2027-07-15 | 2027-08-14 | LIVE AFTER APPLICATION DATE
8 | ITS | AMLR 81(1); AMLAR 41(2) | FIU and AMLA reporting to the EPPO | — | 2026-05-31 | Consultation closed (hearing 27 May 2026) | 2026-08-31 | 2026-11-30 | n/a | 2026-12-20 | 2026-09-30 | 2027-03-30 | n/a | 2027-04-29 | Tight (<3m before application)
9 | ITS | AMLD 31(2) | FIU-to-FIU exchange format | — | 2026-05-31 | Consultation closed (hearing 27 May 2026) | 2026-08-31 | 2026-11-30 | n/a | 2026-12-20 | 2026-09-30 | 2027-03-30 | n/a | 2027-04-29 | Tight (<3m before application)
10 | RTS | AMLD 46(4) | Home-host supervisory cooperation | — | 2026-05-31 | Consultation closed (hearing 28 May 2026) | 2026-08-31 | 2026-11-30 | 2027-02-28 | 2027-03-20 | 2026-09-30 | 2027-03-30 | 2027-06-30 | 2027-07-30 | LIVE AFTER APPLICATION DATE
11 | GL | AMLR 10(4) | Business-wide risk assessment | 2026-04-16 | 2026-07-15 | Consultation open — closes 15 Jul 2026 | 2026-10-15 | n/a | n/a | 2027-07-10 | 2027-01-15 | n/a | n/a | 2027-07-10 | Tight (<3m before application)
12 | GL | AMLR 26(5) | Ongoing monitoring of business relationships (incl. transaction monitoring) | 2026-06-03 | 2026-09-03 | Consultation open — closes 3 Sep 2026 | 2026-12-03 | n/a | n/a | 2027-07-10 | 2027-03-03 | n/a | n/a | 2027-07-10 | Tight (<3m before application)
13 | ITS | AMLR 69(3) | Format for reporting suspicions & providing transaction records (STR) | 2026-07-02 | 2026-09-20 | Consultation open — closes 20 Sep 2026 | 2026-12-20 | 2027-03-20 | n/a | 2027-04-09 | 2027-01-20 | 2027-07-20 | n/a | 2027-08-19 | LIVE AFTER APPLICATION DATE
14 | RTS | AMLD 31(3) | Cross-border information exchange between FIUs | 2026-07-06 | 2026-10-06 | Consultation open — closes 6 Oct 2026 | 2027-01-06 | 2027-04-06 | 2027-07-06 | 2027-07-26 | 2027-02-06 | 2027-08-06 | 2027-11-06 | 2027-12-06 | LIVE AFTER APPLICATION DATE
15 | RTS | AMLAR 11(6) | Central AML/CFT database | — | 2026-09-15 | Consultation planned (SPD: Q2 2026, final Q3 2026) | 2026-12-15 | 2027-03-15 | 2027-06-15 | 2027-07-05 | 2027-01-15 | 2027-07-15 | 2027-10-15 | 2027-11-14 | LIVE AFTER APPLICATION DATE
16 | GL | AMLR 20(3) | Risk variables & risk factors (business relationships / occasional transactions) | — | 2026-12-15 | Consultation planned (SPD: Q3 2026, final Q4 2026) | 2027-03-15 | n/a | n/a | 2027-07-10 | 2027-06-15 | n/a | n/a | 2027-07-10 | Tight (<3m before application)
17 | RTS | AMLD 41(2) | Central contact point — criteria & functions | — | 2026-12-15 | Consultation planned (SPD: Q3 2026, final Q4 2026) | 2027-03-15 | 2027-06-15 | 2027-09-15 | 2027-10-05 | 2027-04-15 | 2027-10-15 | 2028-01-15 | 2028-02-14 | LIVE AFTER APPLICATION DATE
18 | RTS | AMLD 40(2) | Risk profile of obliged entities — non-financial sector | — | 2026-12-15 | Consultation planned (SPD: Q3 2026, final Q4 2026) | 2027-03-15 | 2027-06-15 | 2027-09-15 | 2027-10-05 | 2027-04-15 | 2027-10-15 | 2028-01-15 | 2028-02-14 | LIVE AFTER APPLICATION DATE
19 | GL | AMLD 53(11) | Base amounts of pecuniary sanctions (per breach / entity category) | — | 2026-12-15 | Consultation planned (SPD: Q2 2026, final Q4 2026) | 2027-03-15 | n/a | n/a | 2027-07-10 | 2027-06-15 | n/a | n/a | 2027-07-10 | Tight (<3m before application)
20 | RTS | AMLD 49(14), 50(13) | AML/CFT supervisory colleges (financial & non-financial) | — | 2027-03-15 | Consultation planned (SPD: Q4 2026, final Q1 2027) | 2027-06-15 | 2027-09-15 | 2027-12-15 | 2028-01-04 | 2027-07-15 | 2028-01-15 | 2028-04-15 | 2028-05-15 | LIVE AFTER APPLICATION DATE
21 | GL | AMLR 9(4) | Internal policies, procedures and controls | — | 2027-06-15 | Consultation planned (SPD: Q1 2027, final Q2 2027) | 2027-09-15 | n/a | n/a | 2027-09-15 | 2027-12-15 | n/a | n/a | 2027-12-15 | LIVE AFTER APPLICATION DATE
Blue = hardcoded official dates; blue italic = estimated (AMLA SPD planning quarters). Rows 15–21 are the pipeline: consultations not yet opened — dates are indicative. GL 'live' = later of final publication and 10 Jul 2027 (usual application alignment).
Formulas:
EC adoption (best) = EDATE([AMLA final → EC (best)],Assumptions!$B7)
Scrutiny ends (best) = EDATE([EC adoption (best)],Assumptions!$B8)
LIVE — best case = [Scrutiny ends (best)]+20
LIVE — best case = [EC adoption (best)]+20
EC adoption (real.) = EDATE([AMLA final → EC (real.)],Assumptions!$C7)
Scrutiny ends (real.) = EDATE([EC adoption (real.)],Assumptions!$C8)
LIVE — realistic = [Scrutiny ends (real.)]+30
LIVE — realistic = [EC adoption (real.)]+30
AMLA final → EC (best) = EDATE([Consult. closes],Assumptions!$B6)
AMLA final → EC (real.) = EDATE([Consult. closes],Assumptions!$C6)

## Gantt
Visual timeline (monthly) — C = consultation, P = Level 2 process (best case), S = potential slippage (best → realistic)
Column of 10 Jul 2027 (AMLR application) highlighted in dark red.
# | Instrument | Type | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01
1 | Risk assessment for selection for direct supervision | RTS | P | P | P | P | P | P | P | P | S | S | S
2 | Inherent & residual risk profile of obliged entities (financial sector) | RTS | P | P | P | P | P | P | P | P | S | S | S
3 | Cooperation within supervisory system (direct supervision) | ITS | C | C | P | P | P | P | P | P | P | S | S | S | S
4 | Pecuniary sanctions, administrative measures, periodic penalty payments | RTS |  |  | C | C | P | P | P | P | P | P | P | P | P | S | S | S | S | S
5 | Customer Due Diligence (standard / simplified / enhanced) | RTS |  |  | C | C | C | C | P | P | P | P | P | P | P | P | P | S | S | S | S | S
6 | Business relationships, occasional & linked transactions, lower thresholds | RTS |  |  | C | C | C | C | P | P | P | P | P | P | P | P | P | S | S | S | S | S
7 | Group-wide minimum requirements; third-country branches/subsidiaries | RTS |  |  |  |  | C | C | C | P | P | P | P | P | P | P | P | P | P | S | S | S | S
8 | FIU and AMLA reporting to the EPPO | ITS: ITS; P: P; P: P; P: P; S: P; S: P; S: P; S: P | S | S | S | S
9 | FIU-to-FIU exchange format | ITS: ITS; P: P; P: P; P: P; S: P; S: P; S: P; S: P | S | S | S | S
10 | Home-host supervisory cooperation | ITS: RTS; P: P; P: P; P: P; S: P; S: P; S: P; S: P | P | P | P | S | S | S | S
11 | Business-wide risk assessment | GL |  |  |  |  | C | C | C | C | P | P | P | P | P | P | P | P | P | P | P | P
12 | Ongoing monitoring of business relationships (incl. transaction monitoring) | ITS: GL; P: C; P: C; P: C; S: C; S: P; S: P; S: P | P | P | P | P | P | P | P
13 | Format for reporting suspicions & providing transaction records (STR) | ITS: ITS; P: C; P: C; S: C; S: P; S: P; S: P | P | P | P | P | S | S | S | S
14 | Cross-border information exchange between FIUs | ITS: RTS; P: C; P: C; S: C; S: C; S: P; S: P | P | P | P | P | P | P | P | S | S | S | S | S
15 | Central AML/CFT database | ITS: RTS; S: P; S: P; S: P; S: P | P | P | P | P | P | P | P | S | S | S | S
16 | Risk variables & risk factors (business relationships / occasional transactions) | [14 empty] | P | P | P | P | P | P | P | bar: ITS; S
17 | Central contact point — criteria & functions | ITS: RTS; S: P | P | P | P | P | P | P | P | P | P | P | S | S | S | S
18 | Risk profile of obliged entities — non-financial sector | ITS: RTS; S: P | P | P | P | P | P | P | P | P | P | P | S | S | S | S
19 | Base amounts of pecuniary sanctions (per breach / entity category) | [14 empty] | P | P | P | P | P | P | P | bar: ITS; S
20 | AML/CFT supervisory colleges (financial & non-financial) | ITS: RTS |  |  | P | P | P | P | P | P | P | P | P | P | P | S | S | S | S
21 | Internal policies, procedures and controls | [19 empty] | P | P | P | P | S | S | S | bar: ITS

## Checkpoints
Monitoring calendar — 'checking dates' for compliance planning
Date | What to check / do | Where | Compliance implication (reverse-engineered)
2026-07-15 | Consultation closes: GL business-wide risk assessment — last chance to respond | AMLA Public Consultations | Your BWRA redesign scope will be fixed by these guidelines; start gap analysis on the draft now.
2026-09-03 | Consultation closes: GL ongoing monitoring (incl. transaction monitoring) | AMLA Public Consultations | TM system requirements — vendor/budget cycle for 2027 should assume the draft is near-final.
2026-09-20 | Consultation closes: ITS on STR format & transaction records | AMLA Public Consultations | Single EU STR template: assess whether current reporting systems can generate the AMLA format.
2026-09-30 | AMLA stated it will submit group-wide RTS (16(4)/17(3)) to Commission by this date; check other Q3 finals (sanctions, CDD, 19(9), ITS 15(3)) | AMLA Regulatory Instruments page | Final drafts = de facto specification for build. Freeze design assumptions against the finals.
2026-10-06 | Consultation closes: RTS on FIU cross-border information exchange | AMLA Public Consultations | Mostly authority-facing, but affects data expectations on STR follow-ups.
2026-10-31 | Check Commission adoption of first delegated acts (selection RTS 12(7), risk-profile RTS 40(2) — with EC since Dec 2025) | EUR-Lex / Comitology & delegated acts registers | First hard test of the 3+3+3 model: if these two are not adopted ~10 months after submission, recalibrate all 'realistic' dates.
2026-12-31 | Check Q4 final reports: EPPO ITS, FIU-to-FIU ITS, home-host RTS, CCP RTS, non-financial 40(2), base-amount GL, risk-factor GL | AMLA website | Year-end snapshot for the 2027 compliance budget & programme plan.
2027-01-31 | Monthly OJ watch begins: adoption + scrutiny expiry of CDD RTS, 19(9) RTS, sanctions RTS | Official Journal / EUR-Lex | Best case has CDD RTS live ~Feb-Mar 2027; realistic ~Jul 2027. Track which scenario is materialising.
2027-04-10 | ESCALATION TRIGGER: 3 months before application. Any RTS not yet in OJ will NOT be comfortably live before 10 Jul 2027 | Internal programme review | Decide formally to implement on the basis of AMLA final drafts, documenting the rationale for supervisors.
2027-07-10 | AMLR applies; AMLD6 transposition deadline; EBA guidelines progressively replaced by AMLA instruments | — | Full compliance required on Level 1 even where Level 2 is late. Evidence of good-faith implementation on drafts is your fallback.
2027-12-31 | Check first AMLA selection round for direct supervision (2027) and colleges RTS finalisation | AMLA website | If in scope for direct supervision from 2028: prepare for AMLA data collection and fees.
2028-01-01 | AMLA direct supervision of selected entities begins (first cycle; full readiness mid-2028) | AMLA website | Supervisory relationship changes; JST-style engagement for selected entities.

## Assumptions
Assumptions & method — 'reverse engineering' of Level 2 live dates
Model: consultation close → AMLA review & final draft → Commission adoption → EP/Council non-objection (RTS only) → OJ publication + entry into force.
Stage durations (months) — EDIT THE BLUE CELLS, all dates in 'Timeline' recalculate
Stage | Best case | Realistic | Comment
AMLA review of consultation feedback → final draft to Commission | 3 | 4 | User's assumption: 3 months. AMLA has itself indicated Q3 2026 finals for Q1/Q2 consultations.
Commission rewrite / adoption of delegated or implementing act | 3 | 6 | User's assumption: 3 months. Historically the Commission often exceeds 3 months (translation, legal revision, inter-service consultation).
EP / Council scrutiny (non-objection) — applies to RTS (delegated acts) ONLY | 3 | 3 | Standard 3 months; extendable by a further 3 at EP/Council request — not included even in 'realistic'. ITS (implementing acts) have NO scrutiny period. Guidelines skip Commission and scrutiny entirely.
OJ publication + entry into force (20 days) | 20 days | ~1 month | Best case assumes immediate publication; realistic adds a publication lag.
Guidelines (Level 3): AMLA finalisation after consultation | 3 | 6 | No Commission adoption, no veto. Application date typically aligned with 10 Jul 2027 (comply-or-explain).
Caveats (read before relying on any date)
1. The 3+3+3 model is the USER'S best case. It is optimistic on the Commission stage and silent on the possible +3-month scrutiny extension for RTS.
2. ITS are implementing acts: no EP/Council veto → structurally ~3 months faster than RTS. Guidelines are Level 3: no Commission step at all.
3. Two RTS (risk-profile AMLD 40(2); selection AMLAR 12(7)) skipped an AMLA consultation (EBA had consulted) — final reports published 18 Dec 2025; modelled from that date.
4. Consultation close dates marked '(est.)' are inferred from AMLA's SPD 2026-2028 planning quarters, not announced dates.
5. Industry pressure (e.g. EBF, 7 May 2026, asking for phased implementation of the CDD RTS) may itself shift final calibration and timing.
6. Instruments whose realistic live date falls AFTER 10 Jul 2027 create a compliance paradox: Level 1 applies without its Level 2 detail. Plan on consultation drafts.
Sources (accessed 23 Jul 2026)
AMLA — Regulatory Instruments (overview of mandates & status, last update 3 Jun 2026) |  |  | https://www.amla.europa.eu/policy/regulatory-instruments_en
AMLA — Public Consultations (opening/closing dates) |  |  | https://www.amla.europa.eu/policy/public-consultations_en
AMLR — Regulation (EU) 2024/1624 (Level 1, applies 10 Jul 2027) |  |  | https://eur-lex.europa.eu/legal-content/EN/TXT/?uri=CELEX%3A32024R1624
AMLD6 — Directive (EU) 2024/1640 |  |  | https://eur-lex.europa.eu/legal-content/EN/TXT/?uri=CELEX%3A32024L1640
AMLAR — Regulation (EU) 2024/1620 |  |  | https://eur-lex.europa.eu/legal-content/EN/TXT/?uri=CELEX%3A32024R1620
European Commission — Fighting financial crime |  |  | https://finance.ec.europa.eu/financial-crime_en
EBF feedback on AMLA draft CDD RTS (7 May 2026) |  |  | https://www.ebf.eu/ebf-media-centre/updates/ebf-feedback-on-amla-draft-regulatory-technical-standard-on-customer-due-diligence-under-article-281-amlr/
AMLA SPD 2026-2028 (planned consultation quarters) |  |  | https://www.amla.europa.eu/document/download/27549516-d110-4e91-b1ed-d3552b8f9661_en?filename=AMLA%20SPD%202026-2028.pdf
Legend: blue cells on yellow = editable assumptions / hardcoded inputs. Blue italic dates in Timeline = estimated (not officially announced). All other dates are formulas.